
13.
COSTS AND TIME SCHEDULE

Vessel, including: tiles, supports,

baking system and base



570,000 Euro


Design contract




  77,500 Euro


Subtotal






647,500 Euro

Poloidal field coils, including
:



feedthroughs and cooling system

620,000 Euro


Design contract




  77,500 Euro


Subtotal






697,500 Euro
Anode and Cathode, including

feedthroughs and cooling system

230,000 Euro


Design contract




  50,000 Euro


Subtotal






280,000 Euro

Assembly contract




  90,000 Euro


Pumping, gas feeding  & cntrl.sys.
180,000 Euro 


TOTAL





     1,895,000 Euro

Power supply:
Pinch feeder ‘P’




825,000 Euro

Cathode feeder ‘K’




102,000 Euro

PF feeder ‘A’





181,000 Euro

PF feeder ‘B’





  92,000 Euro

Subtotal





      1200,000 Euro

Electrical work contract


140,000 Euro

TOTAL





      1,340,000 Euro

GRAND TOTAL



     3,235,000 Euro

	
	TOTALS
	Jun-01
	Oct-01
	Mar-02
	May-02
	Sep-02
	Dec-02
	Jul-03
	Jan-04
	Apr-04
	Jul-04

	Money spent
	3,235,000
	
	60,000
	165,000
	382,000
	849,000
	1017,000
	379,000
	181,000
	131,000
	71,000

	
	
	
	
	
	
	
	
	
	
	
	

	LOAD ASSEMBLY
	
	Design
	Contract
	Tender
	Construction
	Check
	Assembly
	
	
	Final check
	Guarantee

	Money spent
	648,000
	
	20,000
	57,500
	57,000
	171,000
	285,000
	
	
	28,500
	28,500

	
	
	
	
	
	
	
	
	
	
	
	

	ASSEMBLY WORK
	
	
	
	
	Tender
	Orders
	Work
	
	Final check
	
	

	Money spent
	90,000
	
	
	
	10,000
	60,000
	
	
	20,000
	
	

	
	
	
	
	
	
	
	
	
	
	
	

	PUMP,GAS,CNTRL
	
	
	
	
	Tender
	Orders
	Assembly
	
	Final check
	
	

	Money spent
	180,000
	
	
	
	20,000
	120,000
	
	
	40,000
	
	

	
	
	
	
	
	
	
	
	
	
	
	

	PF COILS
	
	Design
	Contract
	Tender
	Construction
	
	Check
	Assembly 
	
	Final check
	Guarantee

	Money spent
	697,000
	
	20,000
	57,500
	62,000
	
	372,000
	124,000
	
	31,000
	31,000

	
	
	
	
	
	
	
	
	
	
	
	

	ELECTRODES
	
	Design
	Contract
	Tender
	Construction
	Check
	
	Assembly 
	Check
	Final check
	Guarantee

	Money spent
	280,000
	
	20,000
	30,000
	23,000
	138,000
	
	
	46,000
	11,500
	11,500

	
	
	
	
	
	
	
	
	
	
	
	

	POWER SUPPLY
	
	Design
	
	Tender
	Construction
	Check
	Check
	Assembly
	Final check
	Guarantee
	

	Money spent
	1,200,000
	
	
	
	120,000
	360,000
	360,000
	240,000
	60,000
	60,000
	

	
	
	
	
	
	
	
	
	
	
	
	

	ELECTRICAL WRK
	
	Design
	
	Tender
	Work
	
	
	Final check
	Guarantee
	
	

	Money spent
	140,000
	
	
	20,000
	90,000
	
	
	15,000
	15,000
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